## Dewatering
Risk assessment for Pincroft Weir (Upstream)
Flood Risk Activity: |  |  |  | Temporary dewatering of a main river
Location: |  |  |  | Gathurst Weir on the Lower River Douglas (SD 52990 07902)
Location of environmentally sensitive sites (km / m): |  |  |  | See below
Risk assessment carried out by: |  |  |  | Adam Wheeler
Date: |  |  |  | 2021-05-07
Data and information |  |  |  | Judgement |  |  | Action
Receptor | Source | Harm | Pathway | Probability of exposure | Consequence | Magnitude of risk | Justification for magnitude | Risk management | Residual risk
What is at risk? What do I wish to protect? | What is the agent or process with potential to cause harm? | What are the harmful consequences if things go wrong? | How might the receptor come into contact with the source? | How likely is this contact? | How severe will the consequences be if this occurs? | What is the overall magnitude of the risk? | On what did I base my judgement? | How can I best manage the risk to reduce the magnitude? | What is the magnitude of the risk after management?
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow due to temporary works in channel | Low | High | Medium | This will facilitate the removal of the structure in a flooding event. | The contractor will sign up to EA flood alerts and weather warnings and ensure that all temporary works, men and machinery are removed from the channel in the event of a flood alert. Preparations for a flood event will be made well in advance to allow time to prepare the site and reduce pollution risk. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow due to accidental damage to channel walls | Very low | Medium | Medium | Limiting the area of river that the structure affects reduces the potential for flooding. | The contractor will sign up to EA flood alerts and weather warnings and ensure that all temporary works, men and machinery are removed from the channel in the event of a flood alert. Preparations for a flood event will be made well in advance to allow time to prepare the site and reduce pollution risk. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow | Low | High | Medium | Cofferdam must not significantly reduce channel capacity and must collapse in the event of a flood. | There is a very low risk of out of channel flow unless a severe flood event is expected, in which case all materials, temporary works and euiptment would be removed from the channel prior to the flood. | Low
Fish and aquatic species | Fish or other aquatic species become stranded during dewatering operations | Fish killed during water draw down works | Loss of water resulting in fish deaths | High | High | High | Remove risk by having an appropriate method of working and plans in place for how to manage fish or other aquatic species that may become stranded in the dewatered area. | A fish rescue shall be carried out prior to commencement of de-watering works. Stopper nets shall first be used to prevent fish re-entering the working area. A 20mm mesh screen shall be used on any water pump intakes to prevent damage to any remaining fish, which will be rescued by hand. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement, especially during high flow events | Medium | Medium | Medium | Working in the channel can cause increased sedimentation and other damage, which may be large enough to adversely affect a conservation site or species. | Do not carry out activity within 500m of designated nature conservation sites (there are no designated sites within this radius). Minimal tracking of machinery along the river bed. Appropriate silt mitigation to be inplace in the form of a silt curtain or simmilar downstream of works to reduce sediment impacts in the waterway. | Low
Habitat and species | Spread of non native invasive species and plant and animal diseases | Loss of or damage to habitat or species | Spread of species in the catchment caused by non-native species being disturbed and spread downstream or transported by machinery and equipment to another site | Medium | Medium | Medium | Use of biosecurity measures and good site management will reduce the spread of non-native invasive species | Standard good biosecurity practices will be followed during the activity. This includes ensuring that all machinery and vehicles are thoroughly cleaned and disinfected prior to arriving on site, and are cleaned again after the activity before being taken for use at another site. Himalayan balsam is known to be present on the watercourse and giant hogweed present onsite. Giant hogweed will be sprayed by the contractor and will be sprayed further prior to construction. This will significantly reduce the abundance of giant hogweed and the number of seeds in the soil. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement | Medium | Medium | Medium | Working in the channel can cause increased sedimentation and other damage, which may be large enough to adversely affect a conservation site or species. | There are no breeding sites of protected or priority species known to be within 100 m of the works site. If any protected species are found during the works, works will be halted and the EA will be contacted for advice. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement | Medium | Medium | Medium | Limiting the length of bank being affected reduces the amount of erosion / siltation. | No more than 20m of the river length shall be dewatered. Water pumped from the working area shall be filtered to capture sediment. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | In-channel flow and sediment movement | Medium | Medium | Medium | Limiting the time that the structure is in place, reduces the risk to habitat and species. | The activity shall be limited to a maximum of 8 weeks. | Low
Fish | Direct damage, siltation and erosion | Loss of or damage to species and breeding grounds | Changes in: quantity and dynamics of water flow; structure and substrate of river bed; and structure of riparian zone. | Low | High | Medium | Prohibiting works during breeding periods will greatly reduce the risk to spawning grounds. | Works shall not be carried out during the salmonid or coarse breeding season. | Low
Water quality | Increased siltation caused by working in the river, direct disturbance whilst undertaking construction works or footprint of the finished works. | Increase in sediment load. | Direct run-off from site, or in-channel flow from works within bank. | Medium | Medium | Medium | Will reduce risk due to limited mobilisation of sediment or pollutants. | Minimal tracking of machinery along the river bedworks and will be limited and to the defined working area. No works are to be carried out outside this area, which is small in comparison to the wider water body. Sediment mitigation will be in place in the form of sit curtain or equivilent and monitored to ensure that pollution is controlled. | Low
WFD biological quality elements | Changes in flow, water quality or to habitat | Deterioration of ecological status through loss or harm to biology | Changes in: quantity and dynamics of water flow; connection to groundwater bodies; river connectivity; river depth and width variation; structure and substrate of river bed; and structure of riparian zone. | Medium | Medium | Medium | Limiting the size of the activity reduces the impact on receptors | Dewatering area will be limited to the footprint of the rock ramp, plus a working area for the excavator, to minimise damage to biology. Dewatering works are necessary to minimise pollution as concrete/grano mix will be used in the construction of the ramp. Mixes will be fast setting. | Low
WFD hydromorphology quality elements | Geomorphological processes altered by activity | Deterioration of high morphology status as measured by WFD. | Changes in: quantity and dynamics of water flow; connection to groundwater bodies; river connectivity; river depth and width variation; structure and substrate of river bed; and structure of riparian zone. | Low | High | Medium | Working in the channel can cause increased sedimentation and other damage, which may be large enough to adversely affect the status of the water body. | No activity will take place within 100 m of a high morphology status water body (There are no high morphology status waterbodies in the Ribble catchment) | Low
| Very low | Low | Medium | High
High | 4 | 8 | 12 | 16
Medium | 3 | 6 | 9 | 12
Low | 2 | 4 | 6 | 8
Very low | 1 | 2 | 3 | 4
|  |  |  | Very low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Medium |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | High |  | #REF! | #REF! | #REF! | #REF!
[6 empty] | 3 | 3 | 9 | Medium
[6 empty] | 1 | 3 | 3 | Low
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
| Very low | Low | Medium | High |  | #REF! | #REF! | #REF! | #REF!
Very low | 1 | 2 | 3 | 4 |  | #REF! | #REF! | #REF! | #REF!
Low | 2 | 4 | 6 | 8 |  | 3 | 3 | 9 | Medium
Medium | 3 | 6 | 9 | 12 |  | #REF! | #REF! | #REF! | #REF!
High | 4 | 8 | 12 | 16 |  | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!

## Rock Ramp
Risk assessment for Pincroft Weir (Upstream)
Flood Risk Activity: |  |  |  | Construction of Rock Ramp Style Fish Pass
Location: |  |  |  | Gathurst Weir on the Lower River Douglas (SD 52990 07902)
Location of environmentally sensitive sites (km / m): |  |  |  | See below
Risk assessment carried out by: |  |  |  | Adam Wheeler
Date: |  |  |  | 2021-03-02
Data and information |  |  |  | Judgement |  |  | Action
Receptor | Source | Harm | Pathway | Probability of exposure | Consequence | Magnitude of risk | Justification for magnitude | Risk management | Residual risk
What is at risk? What do I wish to protect? | What is the agent or process with potential to cause harm? | What are the harmful consequences if things go wrong? | How might the receptor come into contact with the source? | How likely is this contact? | How severe will the consequences be if this occurs? | What is the overall magnitude of the risk? | On what did I base my judgement? | How can I best manage the risk to reduce the magnitude? | What is the magnitude of the risk after management?
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow due to temporary works in channel | Low | High | Low | No increase in flood risk is expected | The rock ramp fish pass will not increase flood risk. The bed level upstream is determined by the existing weir and the rock ramp shall not project above that level. | Low
Local population | Increased flood risk | Impact on local population and businesses, damage to property | Out of channel flow due to permanent works | Very low | Medium | Medium | No increase in flood risk is expected. | Hydraulic modelling and Flood Risk Assessment has been carried out for the designs of the works, modelling based on this design shows that there is no increased flood risk. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | Felling of trees/scrub clearance impacts protected species. | High | Low | Medium | Potential for bird nests in trees and scrub that may be felled due access for works. | Any vegetation to be removed as part of the works must be done outside the bird nesting season or assessed by a qualified ecologist. Any trees with potential bat roosts must be assessed. | Low
Habitat and species | Spread of non native invasive species and plant and animal diseases | Loss of or damage to habitat or species | Spread of species in the catchment caused by non-native species being disturbed and spread downstream or transported by machinery and equipment to another site | Medium | Medium | Medium | Use of biosecurity measures and good site management will reduce the spread of non-native invasive species | Standard good biosecurity practices will be followed during the activity. This includes ensuring that all machinery and vehicles are thoroughly cleaned and disinfected prior to arriving on site, and are cleaned again after the activity before being taken for use at another site. Himalayan balsam is known to be present on the watercourse and giant hogweed has been noted onsite.Giant hogweed will be sprayed by the contractor and will be sprayed further prior to construction. This will significantly reduce the abundance of giant hogweed and the number of seeds in the soil. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitats or species | In-channel flow and sediment movement | Medium | Medium | Medium | Working in the channel can cause increased sedimentation and other damage, which may be large enough to adversely affect a conservation site or species. | There are no breeding sites of protected or priority species known to be within 100 m of the works site. If any protected species are found during the works, works will be halted and the EA will be contacted for advice.Sediment mitigation will be in place in the form of sit curtain or equivilent and monitored to ensure that pollution is controlled during construction. | Low
Habitat and species | Siltation and erosion | Loss of or damage to habitat or species | Leacheate from the rock ramp pollutes the stream | Medium | Medium | Medium | Ensuring suitable flow diversion and allowing concrete to set will reduce pollution | Preventing cement leachate from concrete and mortar from entering the stream can be minimised by ensuring effective flow diversion around the working area. Any water which does enter the working area willl be pumped out and filtered through straw bales before re-entering the stream. After construction, the concrete/mortar should be given adequate time to cure before flow diversion is dismantled. | Low
Habitat and species | Geomorphological processes altered by activity | Direct loss of or damage to habitat / species; indirect changes to ability of river to form and sustain habitat | No activity will take place within 100m of a high morphology designated site.L31:N32 | Medium | Medium | Medium | Working in the channel can cause damage and impact on habitats and species. | Geomorphic processes will not be altered by this activity. The channel is highly modified by virtue of being straightened, deepened and embanked. River sediments are impounded by the weir. The rock ramp channel will not alter any geomorphic processes currently ocurring. | Low
Fish | Direct damage, siltation and erosion | Loss of or damage to species and breeding grounds | Changes in: quantity and dynamics of water flow; structure and substrate of river bed; and structure of riparian zone. | Low | High | Medium | Prohibiting works during breeding periods will greatly reduce the risk to spawning grounds. | Works shall not be carried out during the salmonid and coarse fish breeding season. | Low
Water quality | Increased siltation caused by working in the river, direct disturbance whilst undertaking construction works or footprint of the finished works. | Increase in sediment load. | Direct run-off from site, or in-channel flow from works within bank. | Medium | Medium | Medium | Will reduce risk due to limited mobilisation of sediment or pollutants. | Excavation of the bank will be necessary for construction access to the fish pass. In order to reduce the pollution of the river with this material. Post-construction, the bank will be reinstated, graded to a smooth finish and seeded with a suitable native grass seed to encourage rapid re-vegetation. | Low
WFD biological quality elements | Changes in flow, water quality or to habitat | Deterioration of ecological status through loss or harm to biology | Changes in: quantity and dynamics of water flow; connection to groundwater bodies; river connectivity; river depth and width variation; structure and substrate of river bed; and structure of riparian zone. | Medium | Medium | Medium | The works will not affect geomorphological processes. | The rock ramp fish pass is not being constructed within 100 m of a high morphology status water body (There are no high morphology status waterbodies in the Ribble catchment). This waterbody is highly modified. As there is no realistic prospect of weir removal, the construction of a fish pass will not negatively impact upon geomorphology. | Low
| Very low | Low | Medium | High
High | 4 | 8 | 12 | 16
Medium | 3 | 6 | 9 | 12
Low | 2 | 4 | 6 | 8
Very low | 1 | 2 | 3 | 4
|  |  |  | Very low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Low |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | Medium |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | High |  | #REF! | #REF! | #REF! | #REF!
[6 empty] | 4 | 2 | 8 | Medium
[6 empty] | 1 | 3 | 3 | Low
[6 empty] | 3 | 3 | 9 | Medium
[6 empty] | #REF! | #REF! | #REF! | #REF!
| Very low | Low | Medium | High |  | #REF! | #REF! | #REF! | #REF!
Very low | 1 | 2 | 3 | 4 |  | #REF! | #REF! | #REF! | #REF!
Low | 2 | 4 | 6 | 8 |  | 3 | 3 | 9 | Medium
Medium | 3 | 6 | 9 | 12 |  | #REF! | #REF! | #REF! | #REF!
High | 4 | 8 | 12 | 16 |  | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!
[6 empty] | #REF! | #REF! | #REF! | #REF!