## Sheet1
DESIGN PHASE RISK ASSESSMENT
Project | OUR Douglas - Gathurst Rock Ramp Fish Pass
Date | 2021-05-07
Assessor | Adam Wheeler
Organisation | Ribble Rivers Trust
Activity | Risk | Level | Mitigation Approach | Mitigation | Residual risk
DESIGN PHASE
Construction Feasibility | Design places contractor at unreasonable risk | Medium | Choose most accessible area that minimises risks during construction. | Identify risk through design risk assessment, and incorporate in to design selection - chosen design that minimises exposure to river, height and is most accessible | Low
Owner and Public access | Drowning , fall from hights | Medium | Fencing around high risk areas | Public access is via footpath, there is no formal public access at the structure, but it is possible that the public will be able to access the river, however the proposed design will not increase risk. | Low
Ensure Structure Stability | Partial or full Collapse of weir/fish pass | Medium | Utilise design that minimises interference with weir structure, and where possible strengthens design. | The proposed design and location will add structural stability on completion and works will be carried out to mend existing erosion damage to the structure. | Low
Flood Risk | Structure causes flooding of properties | Medium | Ensure design either results in no net increase in risk, or includes actions to mitigate risk | A flood risk assessment has been carried out for the proposed structure, and there is no net increase in flood risk. | Low
CONSTRUCTION
Project overall | Unsatisfactory project | Medium | Employ qualified and experienced contractor and site supervisor. | Ensure that the Client is aware of the need to appoint a suitably experienced, and qualified construction firm. | Low
Stability of Bank and Excavation | Partial or full Collapse of river bank/excavation | High | Ensure contractor includes suitable system for excavation | Appropriate excavation of riverbank for access track into the river to ensure no collapse. Reprofiling and bank mitigation works to be carried out before demob | Low
Stability of Weir | Partial or full Collapse of weir/fish pass | Medium | Ensure risk associated with construction and possible pathways to collapse are understood by contractor. | During works contractor to develop a system to ensure maximum stability of the existing structure | Low
Access to site | Vehicles slide/enter into river | High | Use agreed marked access only, and ensure plant and vehicles are suitable for access | Agree suitable access and ensure that contractor is aware of access restrictions and needs | Low
Access to site | Vehicles access over canal | High | Use agreed marked access only, and ensure plant and vehicles are suitable for access | Agree suitable access and ensure that contractor is aware of access restrictions and needs - Contactor to make appropriate structural assessment of canal swing bridge and plan plant appropriate to access restrictions | Low
Site Flooding | Workers/Vehicles/plant swept away | High | Vacate site prior to expected flood events, have process in place for flash flooding | Maintain contact EA flood forecasters. Make provision for suitable evacuation of site | Low
Working at Height | Falling | High | Remove where possible, or reduce as far as reasonable access to areas where falling risks are present | Ensure areas of risk of falling associated with works are fenced off suitably, provide suitable access into site. | Low
Access to fish pass | Drowning or soaking | High | Design to minimise interaction with moving water as far as reasonably practicable. | Works area to be isolated from flows and dewatered, Wear life jackets, Suitable rescue process included in RAMS (Grab and/or throw rope in place as a minimum and workers are trained in use). | Low
Pollution by contractor | Expose of workers, public and wildlife to harmful substances | Medium | Comply with Environmental Good Practice called for in Specification. | Ensure that best practice and designs are consented/permitted by EA and other authorities. Client to ensure that contractor(s) comply with permit and specification | Low
Exposure to River borne Pollutants | Workers exposed to substances or bacteria | Medium | Ensure Awareness and preventative measures in place | Suitable Welfare Facilitates, workers are aware of hazards | Low
Exposure to COVID-19 | Contacting COVID-19 | High | Ensure Awareness and preventative measures in place - adhering strictly to Construction Leadership Council and UK Government guidance | Suitable PPE and Welfare Facilitates, workers are aware of hazards and adhere strictly to Construction Leadership Council and UK Government guidance | Low
MAINTENANCE
Design for maintenance | Drowning, falling from height | Medium | Utilise design that reduce the need for maintenance, and reduces exposure to working from height. Ensure client is aware of necessity for careful maintenance planning. | The use of a natural process based structure (rock ramp), with minimal opportunity for entrainment of materials, and utilising suitable construction materials will minimise the maintenance requirements to very low | Low